## Release Calendar
Env. | Status/Date | time axis 2016-02-24 to 2016-12-31
FT | Interation #1 | 2016-02-24: UPC Testing; 2016-02-27: UPC Script Testing; 2016-03-03: Report Testing; 2016-03-10: Closed
Update Rec. XDR's Testing
| Interation #2 | 2016-02-26: FT - Drop 2; 2016-03-10: Training Drop 2; 2016-03-14: BVT; 2016-03-19: Closed
| Interation #3 | 2016-02-24: Field Testing - ONDB Rating + MICA Re-Pricing (Including UI Requantification)
[19 empty] | Reports Deployment |  | Field Testing Reports
Deploy Trace Log
| Interation #4 - Tranche 1 | 2016-05-15: Start; 2016-05-16: FT Testing; 2016-05-31: Closed; 2016-06-01: Training
| Interation #4 - Tranche 2 | 2016-06-22: Start; 2016-06-23: FT Testing; 2016-07-23: Closed; 2016-07-27: Training
| Interation #5 | 2016-06-30: Start; 2016-07-01: FT Testing; 2016-09-08: Closed
| Point in Time | 2016-05-01: Start; 2016-05-02: FT Testing; 2016-05-17: Closed
| Case Management | 2016-02-27: FT Installation - Drop 1; 2016-02-29: FT - Drop 1; 2016-03-09: FT and Training - Drop 1; 2016-05-20: FT Installation - Drop 2 Sprint 1; 2016-05-22: FT - Drop 2 Sprint 1; 2016-05-27: FT Installation - Drop 2 Sprint 2; 2016-05-29: FT - Drop 2 Sprint 1, Sprin 2; 2016-06-01: FT and Training - Drop 2 Sprint 1, FT - Drop 2 Sprint 2; 2016-06-03: FT - Drop 2 Sprint 2; 2016-06-08: FT and Training - Drop 2 Sprint 2
Production | Interation #1 | 2016-02-25: Deploy & Execute Update Product Code - Tranche 1; 2016-02-29: Deploy & Execute additional request, after UPC process - Tranche 1; 2016-03-04: PAYG Episode Creation (DST changes for reconciliation) -- Tranche 2; 2016-03-09: Update Product Code Updates (Determine correct rating product) - Tranche 2; 2016-03-14: Execute additional request, after UPC process - Tranche 2; 2016-03-26: Business Report PAYG Episodes; 2016-03-28: Closed
[17 empty] | Iteration 1 Reports |  |  |  | Deploy & Execute script to update XDR for known reason for Non- Reconciled XDRs |  |  |  | PAYG Episode Creation - Tranche 3 (Services not reconciled to 100%) |  |  |  | Update Product Code Updates - Tranche 3 (Services not reconciled to 100%) |  |  | Execute Script for generating additional request, after UPC process - Tranche 3 (Services not reconciled to 100%)
| Interation #2 | 2016-02-29: Deploy & Execute Entity population process for BRT UI (For Iteration 2 drop 1); 2016-03-04: BRT UI Production launch drop 1; 2016-03-16: Deploy & Execute Entity population process for BRT UI (For Iteration 2 drop 2); 2016-03-21: BRT UI Product launch Drop 2 Aligns with Case Managment Drop 1; 2016-03-22: Closed
[7 empty] | Deploy Iteration 2 Drop 1 on production | [15 empty] | Deploy Iteration 2 Drop 2 on production
| Interation #3 | 2016-05-04: Reports - Installation & Config; 2016-05-11: Start; 2016-05-12: Installation, Configuration and Verification; 2016-05-19: End; 2016-10-04: Reports - Install & config; 2016-10-06: Reports and Summary Execution
[74 empty] | Reports and Summary Execution | [13 empty] | Start | Rating and Re-Pricing Production Execution | [132 empty] | End
BVT for iteration 3
| Interation #4 - Tranche 1 | 2016-05-30: Start; 2016-05-31: Deployment; 2016-06-03: BVT; 2016-06-06: BVT (Time Boxed Testing)
Remaining Execution
| Interation #4 - Tranche 2 | 2016-07-23: Deployment; 2016-07-26: Initial Execu.; 2016-08-01: BVT Time Box Testing
Reamaining Execution
| Interation #5 | 2016-09-07: Start; 2016-09-08: Production Deployment; 2016-09-17: Closed
Point in Time
| Case Management | 2016-03-12: BVT Deployment - Drop 1; 2016-03-14: BVT - Drop 1; 2016-03-19: PROD Deployment - Drop 1; 2016-03-21: Production Launch - Drop 1; 2016-06-04: BVT Deployment - Drop 2 Sprint 1; 2016-06-06: BVT - Drop 2 Sprint 1; 2016-06-11: BVT Deployment - Drop 2 Sprint 2; 2016-06-13: BVT - Drop 2 Sprint 2; 2016-06-18: PROD Deployment - Drop 2; 2016-06-20: Production Launch - Drop 2

## Dashboard
Project Delivery | Project Manager | Status
Interation #1 | (Rajiv S) | Closed
Interation #2 | (Rajiv S) | Closed
Interation #3 + Trace Log | (Puneet B) | Closed
Interation #4 - Tranche 1 + Non-Monthly Bill Period | (Amit M) | Closed
Interation #4 - Tranche 2 | (Amit M) | Closed
Interation #5 | (Rajiv S) | Closed
Point in Time | (Rajiv S) | Closed
Case Management | (Rajiv M) | Closed