## Plan
Activity | Start Date | Finish Date | Owner | Remarks
Birch - Globalinx CDR Processing CR | 2016-05-09 | 2016-04-25
SOW Sign-off | 2016-05-09 | 2016-05-09 | Birch, Infogix
Team Allocation | 2016-05-16 | 2016-05-16 | Infogix
Project kick-off | 2016-05-16 | 2016-05-16 | Infogix
Requirement Analysis and Documentation | 2016-05-13 | 2016-05-25
Feed Format and Sample Feed available | 2016-05-13 | 2016-05-13 | Birch
Data Analysis and DFD/FDD Update | 2016-05-16 | 2016-05-18 | Infogix
DFD/FDD Internal Review and Update | 2016-05-19 | 2016-05-20 | Infogix
FDD Review and Update - Birch | 2016-05-23 | 2016-05-25 | Birch, Infogix
FDD Sign-off - Birch | 2016-05-25 | 2016-05-25 | Birch
UAT Test Planning | 2016-05-26 | 2016-06-01
UAT Test Case Documentation | 2016-05-26 | 2016-05-27 | Infogix
UAT Test Case Documentation - Internal Review and Update | 2016-05-30 | 2016-05-30
UAT Test Case Document - Review and Update - Birch | 2016-05-31 | 2016-06-01 | Birch, Infogix
UAT Test Case Document - Sign-off - Birch | 2016-06-01 | 2016-06-01 | Birch
Design, Development, IT, QA Release | 2016-05-26 | 2016-06-01 | Infogix
System Testing - LQA | 2016-06-02 | 2016-06-08 | Infogix
Field Testing (UAT Environment) | 2016-06-09 | 2016-06-14
Environment Setup and Deployment | 2016-06-09 | 2016-06-09 | Infogix
Field Testing | 2016-06-10 | 2016-06-14 | Infogix
UAT Testing | 2016-06-15 | 2016-06-24
UAT Testing - BA | 2016-06-15 | 2016-06-17 | Infogix
UAT Testing - Birch | 2016-06-20 | 2016-06-23 | Birch, Infogix
Customer Acceptance | 2016-06-24 | 2016-06-24 | Birch
Production Deployment | 2016-06-25 | 2016-06-27
Environment Setup and Deployment | 2016-06-25 | 2016-06-26 | Infogix
Go Live | 2016-06-27 | 2016-06-27 | Infogix